## Sheet1
Task | Effort (in days) | Start Date | End Date | Resource
Kick-off meeting | 1 | 2021-04-19 | 2021-04-19 | Team
Defining recruiting criteria | 3 | 2021-04-20 | 2021-04-22 | Team
Designing the study | 3 | 2021-04-21 | 2021-04-23 | UX Researcher
Reviewing the study design | 2 | 2021-04-27 | 2021-04-28 | Team
Writing the discussion guide | 5 | 2021-04-30 | 2021-05-06 | UX Researcher
Building prototype | 10 | 2021-05-05 | 2021-05-18 | Prototyper
Reviewing the discussion guide | 1 | 2021-05-07 | 2021-05-07 | Team
Recruiting outreach | 7 | 2021-05-12 | 2021-05-20 | Recruiter
Piloting the discussion guide | 1 | 2021-05-24 | 2021-05-24 | UX Researcher
Running the sessions | 10 | 2021-05-26 | 2021-06-08 | UX Researcher
Organizing your data | 5 | 2021-06-09 | 2021-06-15 | UX Researcher
Generating the findings | 3 | 2021-06-16 | 2021-06-18 | UX Researcher
Writing your report | 3 | 2021-06-21 | 2021-06-23 | UX Researcher
Delivering the results | 1 | 2021-06-24 | 2021-06-24 | UX Researcher
Reviewing next steps | 1 | 2021-06-28 | 2021-06-28 | Team
Build support | 2 | 2021-07-01 | 2021-07-02 | Team
Formulas:
End Date = WORKDAY([Start Date],[Effort (in days)]-1)